## Sheet1
| Action | Who | Cost | Where To Do This | Notes | Timeline
Basic Set Up | Buy Domain | Client | ~$20/year | https://www.crazydomains.com.au/ https://www.godaddy.com/ | Client Buys Domain (Choose Provider) This is your website, where your name, face and info will appear.
| Create GitHub Account | Client |  | https://github.com/ | Client Creates Account Client Provides Ellen with GitHub Name
| Create Vercel Account | Client |  | https://vercel.com/ | Client Creates Account (Hobby Plan) Use your GitHub Account to create Vercel Account
| Create GitHub Repository | Ellen |  |  | Ellen Creates Repo with Demo Site Ellen Adds Client As Collaborator
| Accept Collaboration on GitHub Repository | Client |  | https://github.com/ | Client Accepts Invitation to Collaborate This is your website code. You can see it and own it. Eventually if you want to edit it, you can do that too.
| Deployment on Vercel | Client |  | https://vercel.com/ | On Vercel, Step 1. Add Project Step 2. Import Repository
| Add Domain On Vercel | Client |  | https://vercel.com/ | Client Adds Domain Name on Vercel
| Give Domain Vercel Details | Client |  | https://www.crazydomains.com.au/ https://www.godaddy.com/ | Adds Vercel Information to Domain Provider
| Add Email Forwarding | Client |  | https://www.crazydomains.com.au/ https://www.godaddy.com/ | Add email forwarding on domain provider info@domain.com > youremail.com
WAIT 24 HOURS
| SSL Certificate | Client |  | https://vercel.com/ | Check SSL Certificates were Created, This is on Vercel, under domains, they should serlf generate
Website Creation | Provide Website Details | Client |  | Email to ellenmarieforbes@gmail.com | Client Provides, Photo, Text and Other Details (i.e. business address, link to appointment booking) This is where you tell me all the details of what you want your website to say. You can deliver this how you want, you can draw a picture, up to you. Include as much detail as you wish.
| Provide Color Scheme | Client |  | https://coolors.co/ | Choose five colours and press export to css. Send me that code.
| Creat Custom Website | Ellen |  |  | Ellen Creates Custom Website
| Website Feedback | Client |  | Email to ellenmarieforbes@gmail.com | Client Reviews, Change Requests
| Website Edits | Ellen |  |  | Ellen Revises Website
Payment ($100)
SEO | Create Google Business Profile | Client |  | google.com/business | Dr [Full Name] – Specialty Location (i.e. Dr Libby Forbes Paediatric Allergist Brisbane) Fill out as many details as you can, opening hours of your clinic, all sub specialty and speciality interests, even interests that relate that aren't strictly your area. Use your exact suburb and city consistently. Put your website in your google business profile.
| Optimise website for SEO | Ellen |  |  | Ellen adds tags, positions text in good headers, basic SEO, mobile friendly, fast load, https schema mark up
| Create Posts On Your Site | Client |  | Email to ellenmarieforbes@gmail.com | Having more pages/info on your site helps. i.e. a few blog posts about certain topics, this will increase your search ranking
| Incoporate Posts into Site | Ellen |  |  | Ellen adds posts into website
| Link Website on Other Platforms | Client |  |  | If in paediatrics, can try to get on mummy blogs, other blogs, try to get your website on other health listings.
Payment ($50)